Lazomis QI

Sepsis Six Compliance Audit — Executive Summary

Quality improvement project (baseline cycle) · Demo NHS Foundation Trust · 1 – 21 July 2026

DEMONSTRATION DOCUMENT. All patients, staff, organisations and results in this summary are fictitious. This document illustrates a Lazomis QI output and must not be used as clinical, governance, appraisal or ARCP evidence.

# Aim

To increase the proportion of patients receiving the complete applicable Sepsis Six bundle from 53% to ≥80% by 31 October 2026, with IV antibiotics within one hour in ≥95% of cases.

# Standard

UK Sepsis Trust Sepsis Six care bundle; NICE NG51 (Sepsis: recognition, diagnosis and early management).

# Headline findings

| Measure | Value |
| --- | --- |
| Records screened | 16 |
| Records included | 15 |
| Fully compliant records | 8 of 15 |
| Overall compliance | 53% |
| Local target | ≥ 90% of the bundle delivered within one hour |

## Lowest-performing criteria

| Criterion | Compliance |
| --- | --- |
| Urine output measured / monitored | 69% |
| IV antibiotics administered within 1 hour | 80% |
| Blood cultures taken before antibiotics | 93% |

# Interpretation

## Headline result

15 of 16 screened records were eligible. 8 of 15 (53%) received every applicable bundle element. One record was excluded (end-of-life pathway).

## Good practice

Oxygen delivery and serum lactate measurement were both delivered in 100% of applicable records — consistently reliable elements.

## Weakest criterion

Urine output measurement was completed in 69% of applicable records, the lowest-performing element and the main driver of incomplete bundles.

# Risks and governance implications

- Urine output not measured or recorded — currently 69%, target ≥ 90% (High priority).

- IV antibiotics not given within one hour — currently 80%, target ≥ 95% (High priority).

- Blood cultures occasionally taken after antibiotics — currently 93%, target ≥ 95% (Medium priority).

- Fluid resuscitation not commenced where indicated — currently 93%, target ≥ 95% (Medium priority).

# Priority actions

| Action | Owner | Target date | Status |
| --- | --- | --- | --- |
| Start the fluid balance chart in ED and hand it over at transfer | S. Okafor | 31 August 2026 | Completed |
| Introduce a nurse-initiated first-dose antibiotic pathway for overnight sepsis | Dr A. Patel | 31 October 2026 | In progress |
| Add a one-hour sepsis countdown prompt to the observation system | Dr J. Nguyen | 30 November 2026 | Planned |
| Weekly time-to-antibiotics run chart circulated to ED and AMU | L. Byrne | 15 September 2026 | In progress |
| Trust-wide sepsis study day | Dr H. Ahmed | — | Deferred |

# Assurance and next steps

- Re-audit planned for 2 November 2026 with a target sample of 40 eligible patients (minimum 30).

- Measure of success: Proportion of eligible patients receiving every applicable bundle element, with time-to-antibiotics reported separately.

- Monitoring: Weekly sample of 5 screened-positive patients from September 2026, plotted on a run chart.

- Process owner named and recorded in the departmental governance log.

This summary supports, but does not replace, clinical judgement. Local policy, formulary and specialist advice should be followed.